## RCA Backlog
Issue Key | Issue Type | Summary | Description | Priority | Status | Assignee | Reporter | Epic Link | Story Points | Sprint | Labels | Components
|  | Address Validation Improvement | Implement enhanced address validation to reduce shipping delays caused by incorrect addresses | High | To Do | Priya Desai | Sonal Khobragade |  |  |  | address-validation,shipping | API Integration
|  | Inventory Synchronization Enhancement | Implement real-time inventory synchronization between e-commerce platform and WMS | High | To Do | Priya Desai | Sonal Khobragade |  |  |  | inventory,sync | WMS Integration
|  | Pick Path Optimization | Implement pick path optimization algorithm to reduce travel time and increase efficiency | Medium | To Do | Priya Desai | Sonal Khobragade |  |  |  | picking,optimization | Warehouse Operations
|  | Research and select address validation API provider | Evaluate available address validation API providers based on accuracy, cost, and integration capabilities | High | To Do | Vikram Patel | Sonal Khobragade | RCA-1 | 5 | Sprint 1 | research,api | API Integration
|  | Design address validation integration architecture | Create technical design for integrating the selected address validation API with the e-commerce platform | High | To Do | Vikram Patel | Sonal Khobragade | RCA-1 | 8 | Sprint 1 | design,architecture | API Integration
|  | Configure API credentials and environment | Set up API keys, endpoints, and test environment for address validation integration | Medium | To Do | Dev Team | Vikram Patel | RCA-1 | 3 | Sprint 2 | configuration | API Integration
|  | Implement real-time address validation on checkout page | Add address validation functionality to the checkout process to catch errors before order submission | High | To Do | Dev Team | Sonal Khobragade | RCA-1 | 13 | Sprint 2 | frontend,validation | E-commerce Platform
|  | Create address correction workflow for existing orders | Implement process for correcting addresses on orders that have already been placed | Medium | To Do | Dev Team | Sonal Khobragade | RCA-1 | 8 | Sprint 3 | workflow,correction | Order Management
|  | Create address validation metrics dashboard | Develop dashboard to track address validation success rates, corrections, and impact on shipping delays | Low | To Do | Dev Team | Vikram Patel | RCA-1 | 5 | Sprint 3 | reporting,metrics | Reporting
|  | Analyze current inventory sync process and identify gaps | Document the current batch process and identify specific points where real-time updates are needed | High | To Do | Suresh Iyer | Sonal Khobragade | RCA-2 | 5 | Sprint 1 | analysis,inventory | WMS Integration
|  | Design real-time inventory sync architecture | Create technical design for real-time inventory synchronization between WMS and e-commerce platform | High | To Do | Vikram Patel | Sonal Khobragade | RCA-2 | 13 | Sprint 1 | design,architecture | WMS Integration
|  | Implement inventory change event triggers in WMS | Add event triggers in the WMS to detect inventory changes (receipts, picks, adjustments) | High | To Do | Dev Team | Vikram Patel | RCA-2 | 8 | Sprint 2 | wms,events | WMS Integration
|  | Develop inventory sync message queue | Implement message queue system to handle high-volume inventory updates reliably | High | To Do | Dev Team | Sonal Khobragade | RCA-2 | 13 | Sprint 2 | queue,messaging | Middleware
|  | Update e-commerce platform to consume real-time inventory updates | Modify e-commerce platform to process inventory updates from message queue and update product availability | High | To Do | Dev Team | Sonal Khobragade | RCA-2 | 13 | Sprint 3 | ecommerce,integration | E-commerce Platform
|  | Create inventory sync monitoring dashboard | Develop dashboard to monitor sync performance, latency, and error rates | Medium | To Do | Dev Team | Vikram Patel | RCA-2 | 5 | Sprint 3 | monitoring,dashboard | Reporting
|  | Analyze current picking routes and identify inefficiencies | Document current picking patterns, measure distances traveled, and identify optimization opportunities | Medium | To Do | Suresh Iyer | Sonal Khobragade | RCA-3 | 8 | Sprint 1 | analysis,picking | Warehouse Operations
|  | Research pick path optimization algorithms | Evaluate available algorithms for warehouse pick path optimization and select the most appropriate approach | Medium | To Do | Vikram Patel | Sonal Khobragade | RCA-3 | 5 | Sprint 1 | research,algorithm | Warehouse Operations
|  | Create digital warehouse map for algorithm input | Develop accurate digital representation of warehouse layout, including zones, aisles, and bin locations | Medium | To Do | Suresh Iyer | Vikram Patel | RCA-3 | 8 | Sprint 2 | mapping,warehouse | Warehouse Operations
|  | Implement pick path optimization algorithm | Develop and integrate the selected optimization algorithm with the WMS | Medium | To Do | Dev Team | Sonal Khobragade | RCA-3 | 13 | Sprint 2 | algorithm,implementation | WMS Integration
|  | Develop mobile interface for optimized pick paths | Create mobile application interface to display optimized pick paths to warehouse staff | Medium | To Do | Dev Team | Sonal Khobragade | RCA-3 | 8 | Sprint 3 | mobile,ui | Mobile Applications
|  | Create picking efficiency dashboard | Develop dashboard to track picking efficiency metrics, including travel distance, time per pick, and orders per hour | Low | To Do | Dev Team | Vikram Patel | RCA-3 | 5 | Sprint 3 | reporting,metrics | Reporting