## Project Timeline
Task | Start Date | End Date | Owner | Status
Project Kickoff & Charter | 2025-02-02 | 2025-02-03 | Sonal Khobragade | Completed
Data Collection & Incident Log Gathering | 2025-02-04 | 2025-02-07 | Sonal Khobragade | Completed
Root-Cause Workshops & 5 Whys Analysis | 2025-02-08 | 2025-02-12 | Sonal Khobragade | Completed
Fishbone Diagram Drafting | 2025-02-13 | 2025-02-16 | Sonal Khobragade | Completed
As-Is Process Mapping | 2025-02-17 | 2025-02-20 | Sonal Khobragade | Completed
To-Be Process Design | 2025-02-21 | 2025-02-24 | Sonal Khobragade | Completed
JIRA Backlog Configuration & Story Creation | 2025-02-25 | 2025-02-27 | Sonal Khobragade | Completed
JIRA Dashboard & Metrics Setup | 2025-02-28 | 2025-03-02 | Sonal Khobragade | Completed
Test Case Development | 2025-03-03 | 2025-03-06 | Sonal Khobragade | Completed
Final Review, Sign-Off & Handover Prep | 2025-03-07 | 2025-03-10 | Sonal Khobragade | Completed
Define project scope and objectives | 2025-02-02 | 2025-02-02 | Sonal Khobragade | Completed
Identify key stakeholders | 2025-02-02 | 2025-02-02 | Sonal Khobragade | Completed
Draft project charter | 2025-02-02 | 2025-02-03 | Sonal Khobragade | Completed
Conduct kickoff meeting | 2025-02-03 | 2025-02-03 | Sonal Khobragade | Completed
Collect historical order fulfillment data | 2025-02-04 | 2025-02-05 | Sonal Khobragade | Completed
Gather incident logs from last 6 months | 2025-02-04 | 2025-02-06 | Sonal Khobragade | Completed
Interview key operations personnel | 2025-02-05 | 2025-02-07 | Sonal Khobragade | Completed
Categorize and prioritize delay incidents | 2025-02-06 | 2025-02-07 | Sonal Khobragade | Completed
Prepare workshop materials | 2025-02-08 | 2025-02-08 | Sonal Khobragade | Completed
Conduct workshop with operations team | 2025-02-09 | 2025-02-10 | Sonal Khobragade | Completed
Perform 5 Whys analysis on top issues | 2025-02-10 | 2025-02-11 | Sonal Khobragade | Completed
Document findings and root causes | 2025-02-11 | 2025-02-12 | Sonal Khobragade | Completed
Create initial fishbone structure | 2025-02-13 | 2025-02-13 | Sonal Khobragade | Completed
Populate causes by category | 2025-02-14 | 2025-02-15 | Sonal Khobragade | Completed
Review fishbone with stakeholders | 2025-02-15 | 2025-02-16 | Sonal Khobragade | Completed
Finalize fishbone diagram | 2025-02-16 | 2025-02-16 | Sonal Khobragade | Completed
Document current order fulfillment process | 2025-02-17 | 2025-02-18 | Sonal Khobragade | Completed
Create BPMN swimlane diagram | 2025-02-18 | 2025-02-19 | Sonal Khobragade | Completed
Identify bottlenecks and pain points | 2025-02-19 | 2025-02-20 | Sonal Khobragade | Completed
Validate As-Is process with stakeholders | 2025-02-20 | 2025-02-20 | Sonal Khobragade | Completed
Design optimized process flow | 2025-02-21 | 2025-02-22 | Sonal Khobragade | Completed
Add automation opportunities | 2025-02-22 | 2025-02-23 | Sonal Khobragade | Completed
Create To-Be BPMN diagram | 2025-02-23 | 2025-02-24 | Sonal Khobragade | Completed
Review To-Be process with stakeholders | 2025-02-24 | 2025-02-24 | Sonal Khobragade | Completed
Set up JIRA project structure | 2025-02-25 | 2025-02-25 | Sonal Khobragade | Completed
Create epics for major improvement areas | 2025-02-25 | 2025-02-26 | Sonal Khobragade | Completed
Write user stories for process changes | 2025-02-26 | 2025-02-27 | Sonal Khobragade | Completed
Prioritize backlog items | 2025-02-27 | 2025-02-27 | Sonal Khobragade | Completed
Define key metrics to track | 2025-02-28 | 2025-02-28 | Sonal Khobragade | Completed
Create JIRA dashboard layout | 2025-02-28 | 2025-03-01 | Sonal Khobragade | Completed
Configure charts and filters | 2025-03-01 | 2025-03-02 | Sonal Khobragade | Completed
Set up automated reporting | 2025-03-02 | 2025-03-02 | Sonal Khobragade | Completed
Define test strategy | 2025-03-03 | 2025-03-03 | Sonal Khobragade | Completed
Create test cases for process changes | 2025-03-03 | 2025-03-05 | Sonal Khobragade | Completed
Link test cases to requirements | 2025-03-05 | 2025-03-06 | Sonal Khobragade | Completed
Review test cases with stakeholders | 2025-03-06 | 2025-03-06 | Sonal Khobragade | Completed
Compile all project deliverables | 2025-03-07 | 2025-03-07 | Sonal Khobragade | Completed
Conduct final review meeting | 2025-03-08 | 2025-03-08 | Sonal Khobragade | Completed
Obtain stakeholder sign-off | 2025-03-09 | 2025-03-09 | Sonal Khobragade | Completed
Prepare handover documentation | 2025-03-09 | 2025-03-10 | Sonal Khobragade | Completed

## Gantt Chart
Task | Start | End | Duration (days) | % Complete
Project Kickoff & Charter | 2025-02-02 | 2025-02-03 | 2 | 100
Data Collection & Incident Log Gathering | 2025-02-04 | 2025-02-07 | 4 | 100
Root-Cause Workshops & 5 Whys Analysis | 2025-02-08 | 2025-02-12 | 5 | 100
Fishbone Diagram Drafting | 2025-02-13 | 2025-02-16 | 4 | 100
As-Is Process Mapping | 2025-02-17 | 2025-02-20 | 4 | 100
To-Be Process Design | 2025-02-21 | 2025-02-24 | 4 | 100
JIRA Backlog Configuration & Story Creation | 2025-02-25 | 2025-02-27 | 3 | 100
JIRA Dashboard & Metrics Setup | 2025-02-28 | 2025-03-02 | 3 | 100
Test Case Development | 2025-03-03 | 2025-03-06 | 4 | 100
Final Review, Sign-Off & Handover Prep | 2025-03-07 | 2025-03-10 | 4 | 100

## Resource Allocation
Resource | Role | Allocation % | Start Date | End Date
Sonal Khobragade | Business Analyst | 100 | 2025-02-02 | 2025-03-10
Rajesh Kumar | Project Sponsor | 20 | 2025-02-02 | 2025-03-10
Anjali Singh | Project Manager | 50 | 2025-02-02 | 2025-03-10
Priya Desai | Product Owner | 70 | 2025-02-02 | 2025-03-10
Vikram Patel | Business Analyst Lead | 60 | 2025-02-02 | 2025-03-10
Suresh Iyer | Operations SME | 80 | 2025-02-04 | 2025-03-06